**Budget and Key Dates**

**Budget;**

1. Image printing on Materials and installation; $2728.00
2. Installation; $ 900.00
3. Artists image fees; $2,400.00
4. Fees to collage, make files for printing; $1,050.00
5. Curatorial Fees; $2,100.00
6. Sub Total; $9,178.00
7. Contingency 20%; $1,806.00 $1.806.00
8. Total; $11,013.00 $11,013.00

This budget is based on quotes received from accredited suppliers and service operators.

Artist fees listed are for the use of images created and to be paid to each artist involved with the project.

Fees to collage, make files for printing are to cover the costs to generate digital files for all four billboard skins. Approximately 21 hours (5 hours per billboard) **Liaise with Billboard Company** @ $50.00 per hour

Curatorial Fees Approximately 42 hours @ $50.00 per hour.

20% contingency will be used to cover under estimated costs and other unforseen circumstances.

**Key Dates;**

**29th October**; Submit EOI to City of Yarra.

**Mid November**; compile images from Stage 1 of Skyptrait project from Australian and German Artists.

Create appropriate image files for billboard manufacturer.

Consult with City of Yarra to ensure images are appropriate.

**December;** provide Billboard Company with image files to produce the first two billboard skins complete with attachment mechanisms.

**Early January;** take delivery of billboard skin.

**Mid January;** install the first two billboard skins.

**February – June;** compile and select imagery to be used for August installation, in consultation with Skypetrait artists and City of Yarra.

**July;** provide Billboard Company with image files to produce the second two billboard skins complete with attachment mechanisms.

**Late August;** de install the first two billboards andinstall the second two billboard skins.

**February 2016;** de install billboard skins ensuring site is ready for the next project.

Skypetrait is negotiating to send all four-billboard skins to Germany for the exhibition scheduled for February, March 2016 at the Staedtische Gallerei in Baden Württemberg Germany.